## Summary
Hot Product Hunter - WBS |  |  |  | Status Summary
Document version | 0.1 | Status | Draft | Status | Count
Customer | Shintech Academy | Created by | BrSE-Hai Anh | Not Started | 21
Start date | 2026-05-29 | End date | 2026-06-19 | In Progress | 4
Scope | Backend-only: API + collector + database + notification |  |  | Done | 1
|  |  |  | Blocked | 0
Phase | Period | Goal | Status
M1 - Setup & Design | 2026/05/29 - 2026/06/02 | GitHub setup, spec, API spec, WBS | In Progress
M2 - Core Backend | 2026/06/03 - 2026/06/13 | FastAPI, DB, collector, filter, notification | Not Started
M3 - Test & Demo | 2026/06/14 - 2026/06/19 | pytest, bug fix, README, demo script | Not Started
KPI | Formula / Rule | Target | Note
Progress | Done task / Total task | >= 90% by final demo | Update Status in WBS sheet
Critical task blocked | Count blocked tasks | 0 | Escalate to BrSE
Must scope completed | All Must tasks done | 100% | Before final demo

## WBS進捗管理
ID | Phase | Task | Description | Owner | Role | Start | End | Estimate(d) | Status | Priority | Deliverable | GitHub Issue | Notes
1.1 | M1 - Setup & Design | Setup GitHub repository | Tạo repo, branch protection, labels, milestones, project board | Hải Anh | BrSE | 2026/05/29 | 2026/05/30 | 1 | Done | High | GitHub repo ready | #1 | Không push trực tiếp main
1.2 | M1 - Setup & Design | Write requirement spec | Viết spec scope MVP, FR/NFR, in/out scope | Hải Anh | BrSE | 2026/05/30 | 2026/06/02 | 1 | In Progress | High | docs/01_requirement_spec.md | #2
1.3 | M1 - Setup & Design | Write API spec | Định nghĩa endpoint, request/response, error format | Hải Anh | BrSE | 2026/05/30 | 2026/06/02 | 1 | In Progress | High | docs/02_api_spec.md | #3
1.4 | M1 - Setup & Design | Write WBS | Chia task, owner, estimate, output | Hải Anh | BrSE | 2026/05/30 | 2026/06/02 | 0.5 | In Progress | High | docs/03_wbs.md | #4
1.5 | M1 - Setup & Design | Finalize GitHub workflow doc | Ghi rule branch, PR, conflict check, merge | Hải Anh | BrSE | 2026/06/02 | 2026/06/02 | 0.5 | In Progress | Medium | docs/04_github_workflow.md | TBD
2.1 | M2 - Core Backend | Setup FastAPI base project | Tạo app/main.py, router structure, health endpoint | Hai Man | Dev - API | 2026/06/03 | 2026/06/04 | 1 | Not Started | High | GET /health works | TBD
2.2 | M2 - Core Backend | Setup project config | Tạo config.py, .env.example, settings loader | Hai Man | Dev - API | 2026/06/03 | 2026/06/04 | 0.5 | Not Started | High | Config loads from .env | TBD | Không commit real token
2.3 | M2 - Core Backend | Setup SQLite + SQLAlchemy | Tạo database.py, session, base model | VyTuoi | Dev - DB/Test | 2026/06/04 | 2026/06/05 | 1 | Not Started | High | DB connection works | TBD
2.4 | M2 - Core Backend | Create product model | Tạo products model + schema | VyTuoi | Dev - DB/Test | 2026/06/05 | 2026/06/06 | 1 | Not Started | High | products table/schema ready | TBD
2.5 | M2 - Core Backend | Create keyword model/API | GET/POST/DELETE /keywords | Hai Man | Dev - API | 2026/06/05 | 2026/06/07 | 1 | Not Started | High | Keyword CRUD works | TBD
2.6 | M2 - Core Backend | Create product API | GET /products, GET /products/{id}, basic filters | Hai Man | Dev - API | 2026/06/06 | 2026/06/08 | 1.5 | Not Started | High | Product API returns data | TBD
2.7 | M2 - Core Backend | Implement keyword filter service | Match title/raw_content with active keywords | VyTuoi | Dev - DB/Test | 2026/06/07 | 2026/06/08 | 1 | Not Started | High | matched_keywords generated | TBD
2.8 | M2 - Core Backend | Implement duplicate check | URL primary duplicate key; fallback normalized_title + source | VyTuoi | Dev - DB/Test | 2026/06/08 | 2026/06/09 | 1 | Not Started | High | Duplicate record skipped | TBD
2.9 | M2 - Core Backend | Implement base collector interface | Base class/common output schema for collectors | hanhtnh1769 | Dev - Collector | 2026/06/03 | 2026/06/05 | 1 | Not Started | High | Collector returns normalized item list | TBD
2.10 | M2 - Core Backend | Implement X/Twitter collector | Collect by keyword/account using X API | hanhtnh1769 | Dev - Collector | 2026/06/05 | 2026/06/09 | 2 | Not Started | High | X items normalized | TBD | X API token required
2.11 | M2 - Core Backend | Implement ecommerce collector | Scrape real data from at least 1 source; Rakuten/Yahoo/Mercari optional priority | hanhtnh1769 | Dev - Collector | 2026/06/09 | 2026/06/12 | 2 | Not Started | High | At least 1 ecommerce source works | TBD | Mock fallback allowed
2.12 | M2 - Core Backend | Implement collector run API | POST /collectors/run with source_type/source | Hai Man | Dev - API | 2026/06/10 | 2026/06/12 | 1 | Not Started | High | Run summary returned | TBD
2.13 | M2 - Core Backend | Implement Telegram notification | Send notification for new matched item and save history | VyTuoi | Dev - DB/Test | 2026/06/10 | 2026/06/12 | 1.5 | Not Started | High | Telegram message sent + DB log | TBD
2.14 | M2 - Core Backend | Implement notification APIs | POST /notifications/test, GET /notifications | VyTuoi | Dev - DB/Test | 2026/06/12 | 2026/06/13 | 1 | Not Started | Medium | Notification APIs work | TBD
3.1 | M3 - Test & Demo | Write pytest for filter logic | Unit test keyword matching cases | VyTuoi | Dev - DB/Test | 2026/06/14 | 2026/06/15 | 0.5 | Not Started | High | pytest passes | TBD
3.2 | M3 - Test & Demo | Write pytest for duplicate check | Unit test URL duplicate and fallback case | VyTuoi | Dev - DB/Test | 2026/06/14 | 2026/06/15 | 0.5 | Not Started | High | pytest passes | TBD
3.3 | M3 - Test & Demo | API integration test/manual checklist | Check health/products/keywords/collectors/notifications endpoints | Hai Man | Dev - API | 2026/06/15 | 2026/06/16 | 1 | Not Started | High | API checklist OK | TBD
3.4 | M3 - Test & Demo | Bug fixing round | Fix bugs from API/collector/notification test | All | All | 2026/06/16 | 2026/06/17 | 1 | Not Started | High | No critical bug remains | TBD
3.5 | M3 - Test & Demo | Write README setup/run guide | Install, env, run server, run test, demo command | Hải Anh | BrSE | 2026/06/17 | 2026/06/18 | 0.5 | Not Started | Medium | README updated | TBD
3.6 | M3 - Test & Demo | Prepare demo script | End-to-end demo: add keyword, run collector, verify DB/API/Telegram | Hải Anh | BrSE | 2026/06/18 | 2026/06/19 | 0.5 | Not Started | High | Demo scenario ready | TBD
3.7 | M3 - Test & Demo | Final review and submission | Check WBS/spec/API/README/code status | All | All | 2026/06/19 | 2026/06/19 | 0.5 | Not Started | High | Submission ready | TBD

## Team
Member | Role | GitHub username | Main responsibility | Notes
Hải Anh | BrSE / Leader | Hải Anh | Docs, WBS, API spec, GitHub management, PR review, demo script | Need confirm real GitHub username
Hai Man | Dev - API | Hai Man | FastAPI base, product API, keyword API, collector run API | Need confirm real GitHub username
hanhtnh1769 | Dev - Collector | hanhtnh1769 | X/Twitter collector, ecommerce collector interface/scraping
VyTuoi | Dev - DB/Test/Notification | VyTuoi | SQLite/SQLAlchemy models, duplicate check, Telegram notification, pytest

## Risks_Issues
ID | Type | Risk / Issue | Impact | Mitigation / Next action | Owner | Status
R-001 | Risk | X API token/quota không đủ cho demo | Collector X có thể fail hoặc bị limit | Chuẩn bị sample/mock fallback; ecommerce collector vẫn demo được | hanhtnh1769 | Open
R-002 | Risk | Ecommerce site block scraping hoặc HTML thay đổi | Parser có thể fail | Implement collector interface; real scraping tối thiểu 1 source; mock fallback | hanhtnh1769 | Open
R-003 | Risk | GitHub username của member chưa đúng format | Invite/assign task có thể sai | Confirm username thật, update Team sheet | Hải Anh | Open
R-004 | Issue | Project name chính thức chưa chốt | Docs có thể cần rename sau | Dùng Hot Product Hunter as working title | Hải Anh | Open
R-005 | Risk | Token/secret bị commit nhầm | Security issue | Use .gitignore, .env.example, code review PR | All | Open
R-006 | Risk | Scope quá rộng nếu làm đủ 3 ecommerce sites | Delay M2 | Must: 1 source real scraping; Should: source 2/3 | BrSE | Open